## Tasks
TaskID | StoryPointID | Task/Story Point Description | Priority | Assinged To | Est. Time | Start Date | End Date | Status | Comments
1 |  | Complete the pending things of "Register GroceryKit" Form/Page | Urgent | M.Badar | 20h | 2014-01-04
| 1.1 | When Save button is pressed, no Validation Message is there | Urgent | M.Badar
| 1.2 | When user input some value in Food Cost, that value is automatically filled in all the next fields of Cost/Earnings | Urgent | M.Badar
| 1.3 | Identify the missing areas of this form which need to be completed | Urgent | M.Badar
| 1.4 | Unit Testing of this form (When completed) | Medium | Laique
| 1.5 | Final Testing | Medium | Kashif Sb.
2 |  | Define a new page "Search GroceryKit" through which user can search GroceryKits on the basis of different Parameters | Urgent | Laique | 15h | 2014-01-04
| 2.1 | Give Domain Knowledge of GroceryKit to Mr. Laique | Urgent | Kashif Sb. |  | 2014-01-04
| 2.2 | Share existing code with Mr. Laique to get handy with architecture & code. Help him to understand all the code | Urgent | M.Badar
| 2.3 | Write necessary services / Service methods for Search GroceyKit page. If there is need of modifying existing one then modify it to meet business need | High | M.Badar
| 2.4 | Define a rough sketch of Search Form (for sarching records of Grocery Kit) having necessary filters on it | Urgent | Kashif Sb.
| 2.5 | Define a new Form for Searching Records of Grocery Kit on the basis of some search Parameters | Urgent | Laique
| 2.6 | Integrate this newly designed form with undelying services to complete this page | Urgent | Laique
| 2.7 | Final Testing | High | Kashif Sb.
3 |  | Import existing data of GroceryKit Forms using Excel Sheets | High | Kashif Sb. | 25h | 2014-01-04
| 3.1 | Define an Excel Sheet format (identifying column names of fields only plus their sequence) for Grocery Kit | Urgent | Kashif Sb. |  | 2014-01-04
| 3.2 | Fill that excel sheet with original data which needs to be imported | High | M.Badar
| 3.3 | Define a new Service "ImportExport", which should contain a method to pick data from Excel sheet | High | M.Badar
| 3.4 | Save this picked data (int Story point 3.2) into corresponding Database Tables as Transactions | High | M.Badar
| 3.5 | Define a Front End Page through which user can Import data of Excel Sheet | Low | Laique
| 3.6 | If there are some problems during this Data import activity, then Prompt that message to user by mentioning erroneous records | Low | M.Badar
| 3.7 | Final Testing | Medium | Kashif Sb.
4 |  | Study well "GitHub" ( Open Source Versioning Control system ), and configure it to work in a Team environement | Urgent | M.Badar | 5h |  |  | 60%
| 4.1 | Create a GITHub account |  | M.Badar |  |  |  | 100%
| 4.2 | Create BitBucket Account & Attach it with GIT Account |  | M.Badar |  |  |  | 100%
| 4.3 | Create an Atlassian Account and use it for BitBucket and GIT Account |  | M.Badar |  |  |  | 100%
| 4.5 | Install Client Software "Source Tree" for performing GITHub commands in GUI way (instead of Command Line methodology) |  | M.Badar |  |  |  | 100%
| 4.6 | Understand working of this Client Software, and Upload at least "Tasks-GroceryKit" excel file | [5 empty] | 100%
| 4.7 | Verify whether Team members defined are working properly, by sending them emails
| 4.8 | Upload now the complete project and provide access to Team Members